## Start here
The 4Sync Method Companion Toolkit
Blank templates and filled examples for the five core records
Rahul Kulkarni and Rashmi Kulkarni, PPS Consulting India
Toolkit edition: October 2026, for the second edition
Use these records in the system your team already trusts. They describe five functions; they do not require five new documents. The filled entries continue Meera’s fictional packaging business. Names, quantities and response times are teaching details, not client outcomes or universal limits.
Start with one recurring problem. Agree the owner, authority and support before trying a new arrangement. Replace the example names and timings with agreements the people doing the work can actually use.
How to use this workbook
Each record has its own sheet: one column for each field in the book, one row for each entry.
The shaded rows on each sheet are the book’s filled example, from Meera’s fictional packaging business. Write your own entries in the white rows below them, and delete the example when you no longer need it.
Keep the book’s field names, so your team and the book use the same words. Adapt timings, authority and acceptance criteria to your business.
Record | The question it answers | Sheet
Direction Log | What matters now? | Open Direction Log
Load Board | What can move? | Open Load Board
Decision Log | Why was this choice made? | Open Decision Log
Triage Ladder | Who responds to an exception? | Open Triage Ladder
Change Log | What should change next? | Open Change Log
Latest edition: https://www.ppsconsulting.biz/insights/4sync
For readers of The 4Sync Method: Build a Business That Depends Less on You, second edition.
Free to use and adapt within your own business. Please don’t sell it or publish it as your own. © 2026 Rahul Kulkarni and Rashmi Kulkarni.

## Direction Log
Direction Log
What matters now?
Use the Direction Log when people need to agree what matters now, especially after the week changes. It preserves the current commitment and the work that has deliberately moved out of the way.
How to fill it: Write the outcome, reason, owner, evidence of completion, deliberate deferral and latest material change. A few clear sentences can be enough.
Watch for this: A list that only grows is not a direction agreement. When a priority enters, show what it displaces or where the extra capacity comes from.
Check it: Ask a colleague to read the entry without your explanation. Can they identify the current promise, its owner and the work that has moved?
Use the same fields for another entry only when they help someone make or carry a decision. Keep detailed evidence in the underlying record and link to it.
The shaded rows are the book’s filled example. Write your entries in the white rows below.
Outcome | Why it matters | Owner | Evidence of completion | Deliberately deferred | Material change
Dispatch 600 cartons on Wednesday and the remaining 400 on Thursday against the current approved reference and acceptance criteria. | Meet the customer’s earlier partial requirement while retaining the original commitment for the balance. | Arun owns production readiness. Priya confirms and records the customer’s acceptance of the split. | Dispatch records show both quantities and dates. Quality acceptance is recorded. Other customer commitments remain intact. | The internal carton-layout trial moves to next week. Meera accepts that trade-off; its owner is told. | Wednesday Flowcheck agreed the feasible split. Priya updates the customer agreement; Arun informs dispatch.

## Load Board
Load Board
What can move?
Use the Load Board to see whether agreed work can move with the people, capacity and dependencies available. A useful entry tells the next owner what must happen; it does more than label the item red or green.
How to fill it: For each useful entry, record work, owner, current position, capacity or dependency, next move and time. Give blocked work an accepted response owner.
Watch for this: A blocked label is easy to maintain while nobody carries the response. If the promised response time passes, use the agreed route rather than waiting for the next meeting.
Check it: Ask the person receiving the next move what they have accepted. Does their answer match the board?
Use the same fields for another entry only when they help someone make or carry a decision. Keep detailed evidence in the underlying record and link to it.
The shaded rows are the book’s filled example. Write your entries in the white rows below.
Work item | Owner | Current position | Capacity or dependency | Next move and time | Response owner if blocked
First 600 cartons | Arun | Ready for dispatch after the recorded quality release. | Capacity: Wednesday’s agreed slot. | Dispatch lead confirms collection against the customer agreement by 14:00.
Remaining 400 cartons | Arun | Scheduled for Thursday. | Dependency: the reserved production slot remains available. | Confirm readiness at Thursday’s start-of-shift check; raise a material change immediately.
Sample for the next order | Arun | Blocked by an unclear artwork revision. |  | Confirm the applicable approval by 12:30. Hold the affected release and escalate earlier if the production window requires it. | Priya, with Leena covering if required.

## Decision Log
Decision Log
Why was this choice made?
Use the Decision Log when a choice changes a commitment or when its reasoning will matter later. Routine decisions within a familiar boundary can remain brief.
How to fill it: Record the decision, owner and date, reason, meaningful alternative, authority and limits, affected people and evidence to review.
Watch for this: Recording a choice does not authorise it. Where approval or customer acceptance is still required, show the decision as pending.
Check it: Could someone who missed the discussion explain why this option was chosen and what would justify revisiting it?
Use the same fields for another entry only when they help someone make or carry a decision. Keep detailed evidence in the underlying record and link to it.
The shaded rows are the book’s filled example. Write your entries in the white rows below.
Decision | Owner and timing | Reason | Alternative considered | Authority and limits | People to inform | Review evidence
Offer 600 cartons on Wednesday and 400 on Thursday using the available capacity. Retain the original Thursday commitment for the balance. | Priya, after Wednesday’s capacity discussion with Arun and before confirming the revised promise to the customer. | The customer needs part of the order sooner. The full order cannot move forward within current commitments. | Dispatch all 1,000 cartons on Thursday. Advancing the whole order would require a separate decision about other commitments. | The split requires customer acceptance and remains within Priya’s agreed commercial authority. Quality criteria and other customer promises remain unchanged. | Customer contact, production and dispatch. Meera receives the update through the shared record. | Customer acceptance, actual dispatch against both commitments and any effect on other promised work.

## Triage Ladder
Triage Ladder
Who responds to an exception?
Use the Triage Ladder for a recurring exception where people need to recognise the trigger, contain the immediate consequence and reach someone able to respond. Agree it before the next urgent message arrives.
How to fill it: Name the trigger, observer, first action, responder, backup, authority, response expectation and onward route. Confirm that cover has both capacity and access.
Watch for this: An acknowledgement is not acceptance of the response. Ask who is carrying it and when the next decision will be available.
Check it: Give the backup a plausible exception. Can they find the evidence, explain what they may decide and identify when to call for help?
Use the same fields for another entry only when they help someone make or carry a decision. Keep detailed evidence in the underlying record and link to it.
The shaded rows are the book’s filled example. Write your entries in the white rows below.
Trigger and observer | Immediate permitted action | First responder and backup | Response expectation | Decision boundary | Pending response or wider consequence
Arun finds two versions or cannot establish the current customer-approved artwork. | Hold the affected release. Continue unaffected work where safe and feasible. Send the order, competing references and production deadline. | Priya confirms the applicable customer approval. Leena covers her absence with the required access and authority. A technical variation goes to the quality lead, with Samir as the prepared quality backup. | Priya or Leena confirms who has accepted the issue within 15 minutes and gives a decision or an explicit next position within 30 minutes. Escalate sooner when the remaining production window requires it. | Production proceeds only against the current approved reference and acceptance criteria. Obtain quality and customer approval for variations where required. | If the responder cannot meet the agreed time, activate the prepared backup and make the pending commitment visible. An exception beyond delegated commercial authority reaches Meera while options remain.

## Change Log
Change Log
What should change next?
Use the Change Log to turn an observed result into a specific adjustment that someone will test. Record the result honestly, including a failed trial or an explanation that remains uncertain.
How to fill it: Record what happened, the supported explanation, uncertainty, the adjustment, owner and scope, evidence to review and the decision that follows.
Watch for this: Do not rewrite the failed result as a success once the correction works. The earlier consequence explains why the arrangement changed.
Check it: Ask another owner what the next trial is meant to establish. If they describe a different test, clarify the entry before proceeding.
Use the same fields for another entry only when they help someone make or carry a decision. Keep detailed evidence in the underlying record and link to it.
The shaded rows are the book’s filled example. Write your entries in the white rows below.
Observed problem | Best-supported explanation | What remains uncertain | Adjustment to test | Owner and scope | Review evidence | Decision after review
The quality backup acknowledged the exception without completing the assessment. Production lost its slot and the agreed dispatch was missed. | The new variation exceeded the familiar reference. Backup capacity was not confirmed, and acknowledgement was mistaken for accepted work. | Whether the revised route will remain usable when the backup is covering another responsibility. | Keep the proven boundary for the original order type. Assess unfamiliar variations before release. Confirm who accepts an exception, what other work moves during cover and how a pending response is escalated. | Meera sponsors the change. The quality lead owns the response arrangement; Arun and Priya confirm the production and customer consequences. Test on the next suitable order. | Check acceptance of the response, time to assessment, quality release and the customer commitment. Include workload displaced to make cover possible. | Keep, revise or stop the adjustment on the evidence. Do not widen the trial merely because the record has been completed.